## Sheet1
|  |  | CEAO FY 2026-2031 LBR PROGRAM | [12 empty] | (Updated 10/06/2025)
|  | Gray Hi-Lited Are Sold | [14 empty] | TOTAL | MAX
|  |  |  | OFF- | LOCAL | LBR | AWARD | FY/ | BID | [7 empty] | COST | COST | FEDERAL | Estimated | Credit Bridge | Fed/State
PID | DIST | CRS | SFN's | SYSTEM | LET | % | DATE | QT | DATE | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | REMARKS | APPROVED | APPROVED | MAXIMUM | Credit Bridge | Maximum | Exchange
119417 | 9 | ADA-TR 1A-0.68 | 0135046 | Y | X | 100 | 2025-04-02 | 25/4 |  | 2026: 983000 | LICK SKILLET RD D/B | 983000 | 1183000 | 1183000 |  |  | N
117978 | 9 | ADA-TR 29-0.605 | 0134317 | Y | X | 100 | 2026-02-02 | 26/3 |  | 2026: 1326000 | BRUSH CREEK RD D/B | 1326000 | 1574900 | 1574900 |  |  | N
120974 | 9 | ADA-CR 47A-0.144 | 0134252 | Y | X | 95 | 2026-10-01 | 27/2 |  | 2027: 614840 | POPLAR GROVE RD D/B | 647200 | 801640 | 761558 | 97080 |  | Y
115423 | 9 | ADA-CR 100-3.98 OBPP | 0137286 | N | X | 100 | 2026-02-02 | 26/3 |  | 2026: 440000 | OLD 32 D/B | 484000 | 484000 | 484000 |  |  | N
119006 | 1 | ALL-CR 176-4.92 | 0247537 | Y | X | 100 | 2026-05-29 | 26/4 |  | 2026: 1237839 | COLS GROVE-BLUFFTON | 1246000 | 1482900 | 1482900 |  |  | N
115516 | 1 | ALL-CR 270-6.41 | 0247596 | N | X | 95 | 2027-01-01 | 27/3 |  | 2027: 1817350 | MAIN ST | 1913000 | 2213000 | 2102350 | 286950 | 331950 | Y
120459 | 1 | ALL-TR 122-0.71 | 0249750 | Y | X | 95 | 2027-11-19 | 28/2 |  | 2028: 2251040 | ADGATE RD | 2813800 | 3195094 | 3035339.3 |  |  | Y
122116 | 1 | ALL-TR 146-1.64 | 0232343 | N | X | 80 | 2028-01-07 | 28/3 |  | 2028: 1530720 | COPUS RD | 1913000 | 2213400 | 1770720 |  |  | Y
115520 | 3 | ASD-TR 1550-0.50 | 0334987 | Y | X | 95 | 2027-01-01 | 27/3 |  | 2027: 683050 |  | 719000 | 887800 | 843410 | 107850 | 133170 | Y
122497 | 4 | ATB-CR 9-Q | 0430234 | Y | X | 80 | 2028-11-30 | 29/2 |  | 2029: 1575680 | WINDSOR MECH RD | 1969600 | 2269600 | 1815680 |  |  | Y
120450 | 7 | AUG-CR 139-15.08 | 0630527 | N | X | 80 | 2028-03-04 | 28/3 |  | 2028: 2908462 | HAMILTON ST | 3635600 | 4099136 | 3279308.8 |  |  | N
119483 | 11 | BEL-TR 428-0.30 | 0733385 | Y |  | 100 | 2025-12-29 | 26/3 |  | 2026: 829854 | COLEMAN RD | 1093000 | 1306950 | 1306950 |  |  | N
110224 | 9 | BRO-CR 24-8.19/8.35 | 0834807, 0834815 | Y |  | 80 | 2026-04-01 | 26/4 |  | 2027: 1600000 | TRI-COUNTY HWY | 2000000 | 2000000 | 1600000 |  |  | N
109440 | 9 | BRO-CR 62-0.42 | 0833533 | Y |  | 80 | 2025-02-24 | 25/3 | FILED | 2026: 647878 | RIPLEY RD | 822000 | 843588 | 674870 |  |  | N
122120 | 8 | BUT-TR 72-1.304 | 0933635 | Y | X | 95 | 2028-09-01 | 29/1 |  | 2026: 3020798 | SHURZ RD | 3198200 | 3618020 | 3437119 | 479730 | 542703 | N
| 8 | BUT-TR 227-4.140 | 0933473 | Y | X | 95 |  | 30 |  | 2030: 3123262 | DARRTOWN RD | 3700000 | 4170000 | 3961500 | 555000 | 594225 | N
122105 | 7 | CLA-CR 351-6.35 | 1255452 | Y | X | 95 | 2028-11-30 | 29/2 |  | 2029: 2376860 | SELMA PIKE | 2363600 | 2700000 | 2565000 | 354550 | 405000 | N
120681 | 8 | CLE-CR 45-2.45 | 1358502 | Y | X | 100 | 2026-04-02 | 26/4 |  | 2026: 1460000 | FELICITY CEDRON RD | 1460000 | 1729000 | 1729000 |  |  | N
123552 | 8 | CLE-CR 54-0.16 | 1358030 | Y | X | 80 | 2027-12-15 | 28/2 |  | 2028: 263360 | GLANCY CRN MAR | 365800 | 490800 | 392640 |  |  | N
| 8 | CLE-CR 107-1.31 | 1358952 | N | X | 80 |  | 27 |  | 2027: 450240 | SHAYLER RD Rehab | 562800 | 700360 | 560288 |  |  | N
122274 | 8 | CLI-CR 21-6.34 | 1432788 | Y | X | 95 | 2028-01-06 | 28/3 |  | 2028: 574750 | PRAIRIE RD Rehab | 619000 | 767800 | 729410 | 92850 | 115170 | N
116198 | 11 | COL-CR 443-3.51 | 1533401 | N | X | 95 | 2026-01-01 | 26/3 |  | 2026: 845690 | HUNSTON RD | 721000 | 890200 | 845690 | 108150 | 133530 | N
108777 | 5 | COS-CR 365-1 | 1630016 | Y | X | 95 | 2025-06-20 | 26/3 | 2025-06-16 | 2026: 2470000 |  | 2087000 | 2600000 | 2470000 | 390000 | 390000 | N
124065 | 5 | COS-CR 28-0.050 | 1630024 | Y |  | 80 |  | 30 |  | 2030: 2400000 | CR 28 | 3377000 | 3814700 | 3051760 |  |  | N
114951 | 3 | CRA-CR 1-15.38 | 1733370 | Y | X | 95 | 2025-07-01 | 26/1 | 2025-05-22 | 2026: 1143503 | MARION-MELMORE RD | 1157000 | 1380550 | 1311522.5 | 180553 | 207082.5 | N
122085 | 3 | CRA-CR 330-19.98 | 1747495 | N | X | 95 | 2029-03-23 | 29/3 |  | 2029: 983725 |  | 1035500 | 1240826 | 1178784.7 | 155325 | 186123.9 | N
120683 | 12 | CUY-LEE RD | 1833987 | N | X | 80 | 2025-10-31 | 26/2 |  | 2026: 1692400 | CR 8-0.77 Rehab D/B | 4892500 | 5481750 | 4385400 |  |  | N
| 12 | CUY-MILES RD | 1830783 | N | X | 80 |  | 29 |  | 2029: 4000000 | CR 11-12.10 | 5000000 | 5600000 | 4480000 |  |  | N
| 7 | DAR-TR 222-1.410 | 1948962 | Y | X | 80 |  | 30 |  | 2030: 750000 | WOODS RD | 1055000 | 1263250 | 1010600 |  |  | Y
121065 | 6 | DEL-CR 72-3.83 | 2134195 | N | X | 95 | 2028-06-01 | 28/4 |  | 2028: 908865 | CHESHIRE RD | 956700 | 1156700 | 1098865 | 143505 | 173505 | N
115725 | 3 | ERI-CR 13-13.43 | 2230186 | N | X | 80+ | 2026-09-15 | 27/1 |  | 2027: 3062821 | MASON RD Rehab | 3225000 | 3647500 | 3465125 | 237537 | 547125 | N
113793 | 5 | FAI-CR 55-3.319 | 2337258 | Y | X | 95 | 2026-03-27 | 26/3 |  | 2026: 1404100 | HAMBURG RD | 1478000 | 1749700 | 1662215 | 221700 | 262455 | Y
| 5 | FAI-CR 46-1.535 | 2334194 | Y | X | 95 |  | 30 |  | 2030: 1499439 | LIB-19 BASIL RD | 1776000 | 2076000 | 1972200 | 266400 | 295830 | Y
| 6 | FAY-TR 119-01.65 | 2432684 | Y | X | 95 |  | 29 |  | 2029: 1924610 | MATTHEWS RD | 2025900 | 2328500 | 2212075 | 303900 | 349275 | Y
122193 | 2 | FUL-CR 27MO-0.20 | 2635399 | Y | X | 95 |  | 29 |  | 2029: 692835 |  | 729300 | 900160 | 855152 | 109395 | 135024 | Y
| 10 | GAL-TR 420-0.00 | 2742330 | Y | X | 80 |  | 28 |  | 2028: 1980900 |  | 2476100 | 2823750 | 2259000 |  |  | N
119138 | 12 | GEA-CR 607-125 | 2830493 | N | X | 95 | 2026-12-04 | 27/2 |  | 2026: 1015550 | PETTIBONE RD | 870000 | 1069000 | 1015550 | 130500 | 160350 | Y
| 12 | GEA-TR 187-7.69 | 2830515 | Y | X | 95 |  | 30 |  | 2030: 1067325 | STAFFORD RD | 1265000 | 1504750.5263 | 1429513 | 189750 | 214426.95 | Y
122137 | 8 | GRE-CR 69-3.52 | 2930331 | Y | X | 80 | 2028-07-06 | 29/1 |  | 2029: 2687680 |  | 3359600 | 3795562 | 3036449.6 |  |  | N
120845 | 5 | GUE-CR 35-9.21 | 3030547 | Y | X | 80 | 2027-07-01 | 28/1 |  | 2028: 2386080 |  | 2982600 | 3380860 | 2704688 |  |  | Y
122106 | 5 | GUE-TR 9420-0.11 | 3034968 | Y | X | 80 | 2028-04-03 | 28/4 |  | 2028: 442480 |  | 553100 | 688719 | 550975.2 |  |  | Y
123526 | 8 | HAM-CR 374-2.93 | 3134156 | N | X | 80 | 2028-09-04 | 29/1 |  | 2029: 337680 | NEWTOWN RD Rehab | 422100 | 547100 | 437680 |  |  | N
120545 | 8 | HAM-CR 239-8.28 | 3137384 | N | X | 80 | 2026-04-16 | 26/3 |  | 2026: 2884800 | WINTON RD D/B | 3606000 | 4066600 | 3253280 |  |  | N
105349 | 8 | HAM-WHV New Viaduct Construction | 3137082 | N |  | 80 | 2026-09-03 | 27/1 |  | 2027: 5000000 | CR 457A-0.00 Western Hills | 6250000 | 6250000 | 5000000 |  |  | N
124115 | 1 | HAN-CR 40-2.620 | 3231607 | Y | X | 95 |  | 30 |  | 2030: 1330000 | HAN CR 40 | 1576000 | 1862400 | 1769280 | 236400 | 265392 | Y
120881 | 1 | HAR-CR 25-1.60 | 3346056 | Y | X | 80 | 2029-02-28 | 29/3 |  | 2029: 915280 |  | 1144100 | 1365715 | 1092572 |  |  | Y
115174 | 11 | HAS-CR 5-6.14 | 3431886 | Y |  | 80+ | 2027-01-01 | 27/3 |  | 2027: 3850201 | OLD HOPEDALE RD | 3721000 | 4193100 | 3983445 | 43665 | 43665 | N
119482 | 11 | HAS-TR 340-34.04 | 3430960 | Y | X | 100 | 2026-05-01 | 26/4 |  | 2026: 1131100 | ELK RUN RD | 1014000 | 1216100 | 1216100 |  |  | N
122086 | 9 | HIG-CR 17-1.08 | 3631044 | Y | X | 80 | 2028-10-02 | 29/2 |  | 2029: 1170560 |  | 1463200 | 1732687 | 1386149.6 |  |  | N
112312 | 10 | HOC-CR 174-0.30 | 3731731 | Y | X | 80 | 2023-12-07 | 24/1 |  | 2026: 842400 | CREAMERY HILL D/B Rehab | 1053000 | 1260950 | 1008760 |  |  | Y
| 10 | HOC-CR 361-0.030 | 3731693 | Y | X | 80 |  | 30 |  | 2030: 800000 | ROCKY BOOTS WAY | 1126000 | 1344900 | 1075920 |  |  | Y
121710 | 11 | HOL-CR 19-5.84 | 3830713 | Y | X | 95 | 2027-07-01 | 28/1 |  | 2028: 1764245 |  | 1857100 | 2157100 | 2049245 | 278565 | 323565 | N
121038 | 3 | HUR-TR 51-2.98 | 3948498 | Y | X | 80 | 2027-12-15 | 28/2 |  | 2028: 1440640 | GREENWICH MILAN TL RD | 1800800 | 2100800 | 1680640 |  |  | N
119355 | 3 | HUR-CR 65-2.11 | 3936511 | Y | X | 100 | 2026-12-15 | 27/2 |  | 2026: 2185000 | PERU WEST SECT LINE D/B | 2185000 | 2503500 | 2503500 |  |  | N
113802 | 3 | HUR-TR 182-1.16 | 3939308 | Y | X | 80+ | 2025-08-19 | 26/2 | 2025-08-08 | 2026: 1024100 | VESTA RD D/B | 1043000 | 1249450 | 1186977.5 | 155102 | 187417.5 | N
113811 | 3 | HUR-CR 183-0.80 | 3934772 | Y | X | 95 | 2025-08-29 | 26/1 | FILED | 2026: 1937050 | CHENANGO RD D/B | 1739000 | 2039000 | 1937050 | 260850 | 305850 | N
119414 | 3 | HUR-CR 185-0.71 | 3938786 | Y | X | 80 | 2026-12-30 | 27/2 |  | 2027: 1484000 | COOK RD D/B | 1855000 | 2155000 | 1724000 |  |  | N
121027 | 3 | HUR-CR 242-0.15 | 3931781 | Y | X | 95 | 2027-12-15 | 28/2 |  | 2028: 1924605 | OLD US20 | 2025900 | 2328490 | 2212065.5 | 303885 | 349273.5 | N
122079 | 3 | HUR-TR 198-0.12 | 3936244 | Y | X | 95 | 2028-10-06 | 29/2 |  | 2029: 2031575 |  | 2138500 | 2452353 | 2329735.35 | 320785 | 367852.95 | N
117979 | 9 | JAC-TR 216-0.11 | 4032624 | Y | X | 100 | 2026-03-02 | 26/3 |  | 2026: 743000 | SPRINGER RD D/B | 743000 | 916600 | 916600 |  |  | N
119418 | 9 | JAC-TR 230-3.09 | 4032748 | Y | X | 100 | 2025-06-25 | 26/1 | 2025-06-17 | 2026: 569367 | BIG RUN RD D/B | 765000 | 943000 | 943000 |  |  | N
122806 | 9 | JAC-TR 517-2.07 | 4035232 | Y | X | 95 | 2027-01-01 | 27/3 |  | 2027: 867550 | RAMEY DR D/B | 956700 | 1156700 | 1098865 | 143505 | 173505 | Y
119484 | 11 | JEF-CR 6-0.00 | 4133048 | N | X | 80 | 2025-07-01 | 26/1 |  | 2026: 1145840 | BLAIRMONT RD | 1202000 | 1432300 | 1145840 |  |  | Y
| 11 | JEF-CR 74-0.478 | 4130790 | Y | X | 80 |  | 30 |  | 2030: 1360000 | GOULDS RD | 1913000 | 2213000 | 1770400 |  |  | N
120593 | 5 | KNO-CR 89-0.13 | 4232585 | Y | X | 95 | 2028-03-31 | 28/3 |  | 2028: 1871120 | KINNEY RD | 1969600 | 2269600 | 2156120 | 295440 | 340440 | Y
115515 | 5 | KNO-TR 369-0.67 | 4236580 | Y | X | 95 | 2027-03-31 | 27/3 |  | 2027: 935750 | COOKE RD | 985000 | 1185000 | 1125750 | 147750 | 177750 | N
121991 | 5 | KNO-TR 385-00.03 | 4237617 | Y | X | 95 | 2028-04-03 | 28/4 |  | 2028: 1016200 | MILE CREEK RD | 1069700 | 1280158 | 1216150.1 | 160455 | 192023.7 | Y
117744 | 12 | LAK-CR 106-0.40 | 4348923 | Y | X | 80 | 2025-04-01 | 25/4 |  | 2026: 763224 | MANCHESTER RD | 954000 | 1154000 | 923200 |  |  | Y
122361 | 12 | LAK-TYLER BLVD | 4342828, 4342879 | N | X | 95 | 2026-10-01 | 27/2 |  | 2026: 259040; 2027: 2112208 | LAK CR 516 1.00/1.425 | 2964000 | 3471800 | 3298210 | 494732 | 494732 | N
120590 | 5 | LIC-TR 56-0.45 | 4534840 | Y | X | 95 | 2027-12-31 | 28/2 |  | 2028: 720765 | DUTCH CROSS RD | 758700 | 935440 | 888668 | 113805 | 140316 | Y
122097 | 5 | LIC-TR 243-4.38 | 4536592 | Y | X | 95 | 2028-04-03 | 28/4 |  | 2028: 1444770 | MONTGOMERY RD | 1520800 | 1798921 | 1708974.95 | 228120 | 269838.15 | Y
118428 | 3 | LOR-TR 42-2.27 | 4733797 | Y | X | 100 | 2025-11-15 | 26/2 |  | 2026: 961000 | BURSLEY RD D/B | 1061000 | 1270150 | 1270150 |  |  | N
119983 | 3 | LOR-M 43-1.57 | 4735943 | Y | X | 100 | 2026-04-15 | 26/4 |  | 2026: 546000 | GRIGGS RD Rehab | 649000 | 700800 | 700800 |  |  | N
114030 | 3 | LOR-TR 44-8.23 | 4736303 | Y | X | 95 | 2025-08-01 | 26/1 |  | 2026: 1131944 | HAWLEY RD D/B | 1159000 | 1382850 | 1313707.5 | 162480 | 207427.5 | N
| 3 | LOR-M 87-2.08 | 4740483 | N | X | 95 |  | 29 |  | 2029: 823400 |  | 866700 | 1065042 | 1011789.9 | 130020 | 159756.3 | N
124177 | 2 | LUC-CR 71-0.310 | 4831004 | N | X | 95 |  | 30 |  | 2030: 679250 | KING RD | 715000 | 883000 | 838850 | 107250 | 125827.5 | Y
103815 | 6 | MAD-TR 66-2.35 | 4931416 | Y | X | 95 | 2026-05-01 | 26/4 |  | 2026: 1558000 | DYER RD D/B | 750000 | 1775000 | 1686250 | 59824 | 266250 | Y
121512 | 6 | MAD-CR 71-4.16 | 4932471 | N | X | 80 | 2026-02-02 | 26/3 |  | 2026: 504450 | SPRING VALLEY RD D/B | 481000 | 606000 | 575700 | 79650 | 79650 | Y
115654 | 6 | MAD-CR 133A-0.13 | 4931955 | Y | X | 95 | 2024-06-10 | 24/4 |  | 2026: 1376550 | CHESELDINE RD Rehab D/B | 1449000 | 1716350 | 1630533 | 217350 | 257453 | Y
122134 | 6 | MAD-CR 62-1.10 | 4931351 | Y | X | 80+ | 2029-05-25 | 29/4 |  | 2029: 3207670 | ROBISON RD | 3376500 | 3814150 | 3429728 | 0 | 0 | Y
118999 | 4 | MAH-CR 90 0.34 | 5034140 | Y | X | 100 | 2025-04-09 | 25/4 |  | 2026: 1226038 | BERLIN STATION RD | 1867000 | 2428200 | 2428200 |  |  | N
120816 | 4 | MAH-CR 119-2.10 | 5030129 | N | X | 80 | 2027-12-16 | 28/2 |  | 2028: 605040 | FOUR MILE RUN RD | 756300 | 932610 | 746088 |  |  | N
123939 | 4 | MAH-CR 28-5.79 | 5044251 | Y | X | 80 | 2029-04-02 | 29/4 |  | 2029: 562715 | MIDDLETOWN RD | 703400 | 869081 | 695264.8 |  |  | N
121540 | 6 | MAR-CR 148B-1.20 | 5132509 | Y | X | 100 | 2025-07-01 | 26/1 |  | 2026: 6405; 2027: 604000 | FIRSTENBERGER RD Rehab D/B | 657000 | 813400 | 813400 |  |  | N
121007 | 3 | MED-CR 97-1.50 | 5243076 | N | X | 95 | 2026-05-15 | 26/4 |  | 2026: 643150 | GREENWICH RD Rehab D/B | 677000 | 837400 | 795530 | 101550 | 125610 | N
| 3 | MED-CR 102-2.190 | 5235065 | Y | X | 95 |  | 30 |  | 2030: 1140000 | SANFORD RD | 1351000 | 1603650.5263 | 1523468 | 202650 | 228520.2 | Y
117990 | 7 | MER-CR 80-1.10 | 5457750 | Y | X | 100 | 2026-05-01 | 26/4 |  | 2026: 1565149 | SIEGRIST JUTTE RD Rehab | 1963000 | 2263000 | 2263000 |  |  | N
120457 | 7 | MER-CR 236-3.03 | 5431611 | N | X | 80+ | 2027-07-01 | 28/1 |  | 2028: 748505 | ROCKFORD W RD Rehab | 787900 | 970427 | 921905.65 | 118185 | 145564.05 | Y
120506 | 7 | MIA-CR 199-2.56 | 5536197 | N |  | 95 | 2027-07-01 | 28/1 |  | 2028: 4512120 | PIQUA-LOCKINGTON | 4749600 | 5263158 | 5000000.1 | 712440 | 789474 | N
119037 | 10 | MOE-TR 2214-0.06 | 5631114 | Y |  | 100 | 2026-01-01 | 26/3 |  | 2026: 985700 | Rehab | 984000 | 1184000 | 1184000 |  |  | N
| 10 | MOE-TR 562-1.296 | 5635101 | Y |  | 80 |  | 30 |  | 2030: 1400000 | TWP RD 562 | 1970000 | 2270000 | 1816000 |  |  | N
122103 | 7 | MOT-CR 23-0.35 | 5738156 | Y | X | 80 | 2029-03-06 | 29/3 |  | 2029: 2242000 | PREBLE COUNTY LINE | 2802500 | 3182750 | 2546200 |  |  | N
122084 | 10 | MRG-CR 70-1.955 | 5833256 | Y |  | 95 | 2027-10-01 | 28/2 |  | 2028: 957885 |  | 1008300 | 1209545 | 1149067.75 | 151245 | 181431.75 | N
118990 | 5 | MUS-M0007-0.09 | 6036023 | N | X | 95 | 2027-03-31 | 27/3 |  | 2027: 1712850 | FIRST STREET | 1803000 | 2103000 | 1997850 | 270450 | 315450 | N
120694 | 5 | MUS-CR 44-1.69 | 6032133 | N | X | 95 | 2026-10-01 | 27/2 |  | 2027: 1283070 | SALT CREEK RD Rehab | 1350600 | 1603190 | 1523030.5 | 202590 | 240478.5 | N
120724 | 5 | MUS-TR 90-0.84 | 6037399 | Y | X | 95 | 2027-07-01 | 28/1 |  | 2028: 695020 | SLACK RD | 731600 | 902920 | 857774 | 109740 | 135438 | N
115541 | 5 | MUS-TR 492-0.73 | 6040330, 6040357, 6030688 | Y | X | 95 | 2025-03-31 | 25/3 |  | 2026: 1321450 | RAYNER LN | 1391000 | 1649650 | 1567167.5 | 208650 | 247447.5 | Y
122100 | 5 | MUS-TR 196-1.02 | 6032516 | Y | X | 95 | 2028-04-03 | 28/4 |  | 2028: 1710760 | BURNT MILL RD | 1800800 | 2100800 | 1995760 | 270120 | 315120 | Y
120366 | 10 | NOB-CR 62-0.80 | 6135161 | Y |  | 80 | 2027-01-01 | 27/3 |  | 2027: 811200 |  | 1014000 | 1216100 | 972880 |  |  | N
119413 | 10 | NOB-TR 392-0.02 | 6132030 | Y |  | 100 | 2026-01-01 | 26/3 |  | 2026: 461800 | MEADOW LANE D/B | 508000 | 634600 | 634600 |  |  | N
122401 | 10 | NOB-CR 37-4.62 | 16130038 | Y |  | 95 | 2029-01-01 | 29/3 |  | 2029: 831250 |  | 875000 | 1075000 | 1021250 | 131250 | 161250 | N
122192 | 2 | OTT-TR 67-5.71 | 6230253 | Y | X | 95 | 2029-01-01 | 29/3 |  | 2029: 641250 |  | 675300 | 835368 | 793599.6 | 101295 | 125305.2 | Y
113849 | 1 | PAU-TR 33-4.75 | 6333389 | Y |  | 80 | 2026-01-01 | 26/3 |  | 2026: 940000 |  | 1304000 | 1549600 | 1239680 |  |  | N
122109 | 5 | PER-TR 135-0.05 | 6434711 | Y |  | 95 | 2029-04-02 | 29/4 |  | 2029: 1072075 | MONDAY CREEK TWP RD | 928500 | 1128500 | 1072075 | 169275 | 169275 | N
122130 | 6 | PIC-TR 106-3.10 | 6531946 | Y | X | 95 | 2028-09-01 | 29/1 |  | 2029: 687510 |  | 723700 | 893440 | 848768 | 108555 | 134016 | Y
115499 | 9 | PIK-CR 44-0.16 | 6633447 | Y |  | 95 | 2027-04-01 | 27/4 |  | 2027: 1567168 | TURKEY RUN RD | 1391000 | 1649650 | 1567167.5 | 208650 | 247447.5 | N
119422 | 9 | PIK-TR 252-0.02 | 6633889 | Y |  | 100 | 2027-01-01 | 27/3 |  | 2027: 525000 | NEWLAND HILL RD | 437000 | 562000 | 562000 |  |  | N
117984 | 9 | PIK-TR 428-0.04 | 6633455 | Y |  | 100 | 2027-04-01 | 27/4 |  | 2027: 637000 | BEATTY RD D/B | 637000 | 789400 | 789400 |  |  | N
122090 | 9 | PIK-TR 311-01.95 | 6633161 | N |  | 95 | 2028-10-02 | 29/2 |  | 2029: 534660 | VANAKA BANK RD | 562800 | 700363 | 665344.85 | 84420 | 105054.45 | N
118361 | 4 | POR-TR 123B-0.44 | 6730256 | Y | X | 95 | 2025-11-21 | 26/2 |  | 2026: 1297890 | ESWORTHY RD D/B | 1188000 | 1416200 | 1345390 | 178200 | 212430 | N
105556 | 4 | POR-CR 145-5.285 OBPP | 6740448 | N | X | 100 | 2024-09-20 | 25/1 |  | 2026: 1459000 | RAVENNA RD | 1459000 | 1459000 | 1459000 |  |  | N
119501 | 4 | POR-CR 177H-10.092 | 6732569 | Y | X | 95 | 2025-11-28 | 26/2 |  | 2026: 1377073 | NEWTON FALLS RD | 1217000 | 1449550 | 1377072.5 | 217433 | 217432.5 | N
122129 | 4 | POR-TR 250A-0.685 | 6732208 | Y | X | 95 | 2027-04-01 | 27/4 |  | 2027: 1120240 | HOPKINS RD | 979200 | 1179200 | 1120240 | 146880 | 176880 | N
121755 | 4 | POR-SUMMIT/STOW ST PD IMP | 6737498 | N | X | 95 | 2028-07-31 | 29/1 |  | 2029: 1943035 | MR 479-0.734 | 2045300 | 2045300 | 1943035 | 306795 | 306795 | N
114050 | 8 | PRE-TR 216-0.65 | 6841333 | Y | X | 95 | 2025-12-15 | 26/2 |  | 2026: 1023863 | CONCORD FAIRHAVEN D/B | 987000 | 1187000 | 1127650 | 148050 | 178050 | N
120885 | 1 | PUT-CR 11J-0.044 | 6930158 | Y | X | 95 | 2027-12-03 | 28/2 |  | 2026: 935180 |  | 928500 | 1128500 | 1072075 | 147660 | 169275 | N
115517 | 1 | PUT-CR 21H-1.014 | 6933327 | Y | X | 95 | 2027-01-01 | 27/3 |  | 2027: 2239150 |  | 2357000 | 2692700 | 2558065 | 337601 | 403905 | Y
119291 | 3 | RIC-CR 146-0.04 | 7032285 | Y | X | 100 | 2026-04-09 | 26/2 |  | 2027: 820000 | MARION AVE RD | 975000 | 1175000 | 1175000 |  |  | N
120748 | 3 | RIC-TR 185-1.11 | 7030975 | Y | X | 95 |  | 28 |  | 2028: 695020 | SHOUP RD | 731600 | 902920 | 695020 | 109740 | 135438 | Y
117614 | 9 | ROS-CR 92-6.50 | 7135769 | Y | X | 100 | 2025-10-08 | 26/2 |  | 2026: 778960 | NORMAN HILL RD | 628300 | 778960 | 778960 |  |  | N
117609 | 9 | ROS-CR 166-5.88 | 7141106 | Y | X | 100 | 2024-05-02 | 26/1 |  | 2026: 218373 | Rehab | 155300 | 233950 | 233950 |  |  | N
117610 | 9 | ROS-TR 183-7.56 | 7142595 | Y | X | 100 | 2024-05-02 | 26/1 |  | 2026: 172553 | Rehab | 150000 | 225000 | 225000 |  |  | N
117612 | 9 | ROS-CR 184-3.76 | 7142862 | Y | X | 100 | 2024-05-02 | 26/1 |  | 2026: 323842 | Rehab | 288000 | 410000 | 410000 |  |  | N
115500 | 9 | ROS-CR 213-7.81 | 7145071 | Y |  | 80 | 2028-01-01 | 28/3 |  | 2029: 3384800 | MUSGROVE RD | 4231000 | 4754100 | 3803280 |  |  | N
121104 | 2 | SAN-M CHER-0.01 | 7250274 | Y | X | 95 | 2027-02-15 | 27/3 |  | 2027: 1587830 | CHERRY ST | 1671400 | 1971400 | 1872830 | 250710 | 295710 | Y
117981 | 9 | SCI-TR 100-1.90 | 7333021 | Y | X | 100 | 2025-12-11 | 26/2 |  | 2026: 815828 | POND RUN RD | 1211000 | 1442650 | 1442650 |  |  | N
117983 | 9 | SCI-TR 103-0.63 | 7333056 | Y | X | 100 | 2025-10-02 | 26/2 |  | 2026: 973000 | STONY RUN RD | 790000 | 973000 | 973000 |  |  | N
122089 | 9 | SCI-CR 23-0.05 | 7330618 | Y | X | 95 | 2028-10-02 | 29/2 |  | 2029: 1716080 | PIKETON RD | 1806400 | 2106500 | 2001175 | 270960 | 315975 | N
| 2 | SEN-TR 36-8.740 | 7440707 | Y | X | 95 |  | 30 |  | 2030: 1187500 | LIB TR 36 | 1407000 | 1668050.5263 | 1584648 | 211050 | 237697.2 | Y
113819 | 7 | SHE-TR 49-3.59 | 7543166 | Y | X | 95 | 2025-09-02 | 26/2 | 2025-08-28 | 2026: 5000000 | KUTHER RD | 4863000 | 5263158 | 5000000.1 | 515800 | 789473.7 | Y
114325 | 4 | STA-CR 119-1.78 (ROBERTSVILLE AVE) | 7633971 | Y | X | 80 | 2025-09-30 | 26/1 |  | 2026: 743840 | ABANDONED RR Demo | 754000 | 929800 | 743840 |  |  | N
119001 | 4 | STA-NORTHVALE AVE | 7634323 | Y | X | 100 | 2025-12-31 | 26/2 |  | 2026: 912400 | TR 313-1.01 Rehab | 984000 | 1418500 | 1418500 |  |  | N
124471 | 4 | STA-CR 26-6.42 | 7632002 | N | X | 80 | 2030-01-02 | 30/2 |  | 2030: 2556320 | SAWBURG | 2814000 | 3195400 | 2556320 |  |  | N
120795 | 4 | SUM-GLENWOOD DR | 7755058 | N | X | 80 | 2028-04-03 | 28/4 |  | 2028: 2942400 | CR 126-1.14 | 3252700 | 3678000 | 2942400 |  |  | N
117489 | 4 | SUM-SNYDER AVE | 7731019 | N | X | 95 | 2025-12-12 | 26/2 |  | 2026: 1591250 | M0003-1.60 D/B | 1500000 | 1775000 | 1686250 | 225000 | 266250 | N
122580 | 4 | SUM-CR 174-1.73 (WHEATLEY RD) | 7749023 | Y | X | 80 | 2027-07-02 | 28/1 |  | 2028: 840130 | WHEATLEY RD | 854300 | 1050162 | 840129.6 |  |  | N
121730 | 4 | TRU-SALT SPRINGS RD BRIDGE | 7839200 | N | X | 80 | 2028-01-07 | 28/3 |  | 2028: 742800 | CR 72E-12.00 | 928500 | 1128500 | 902800 |  |  | N
114332 | 4 | TRU-WEST MARKET ST | 7835566 | N | X | 80 | 2026-03-31 | 26/3 |  | 2026: 3666000 | Rehab | 4075000 | 4582500 | 3666000 |  |  | N
| 4 | TRU-MCCLEARY JACOBY RD | 7842309 | N | X | 80 |  | 28 |  | 2028: 292640 | CR 201C-11 | 365800 | 490800 | 392640 |  |  | N
114260 | 11 | TUS-CR 62-0.89 | 7930267 | N | X | 80 | 2026-02-16 | 26/3 |  | 2026: 5000000 |  | 6250000 | 6250000 | 5000000 |  |  | N
| 11 | TUS-CR 1-3.278 | 7930003 | N | X | 80 |  | 30 |  | 2030: 5000000 | OXFORD RD | 6250000 | 6250000 | 5000000 |  |  | N
121507 | 6 | UNI-CR 67-3.408 | 8031401 | Y | X | 95 | 2027-01-15 | 27/3 |  | 2028: 3337350 | STRENG RD | 3513000 | 3964300 | 3766085 | 526950 | 594645 | N
115518 | 1 | VAN-CR 124-0.14 | 8137137 | N |  | 80 | 2027-01-01 | 27/3 |  | 2027: 866560 | MIDDLE POINT RD | 1159000 | 1382850 | 1106280 |  |  | N
| 10 | VIN-TR 34J-1.50 | 8233756 | Y | X | 80 |  | 27 |  | 2027: 358400 | SBP | 448000 | 573000 | 458400 |  |  | Y
120369 | 8 | WAR-TR 147-0.47 | 8333076 | Y | X | 100 | 2026-01-05 | 26/3 |  | 2026: 540000 | GROG RUN RD Rehab | 415000 | 540000 | 540000 |  |  | N
120673 | 8 | WAR-CR 182-0.10 | 8333475 | Y | X | 95 | 2027-01-19 | 27/3 |  | 2027: 2146335 | Rehab | 2259300 | 2585228 | 2455966.6 | 338895 | 387784.2 | Y
122837 | 8 | WAR-CR 24-0.12 | 8330824 | Y | X | 95 | 2027-12-14 | 28/2 |  | 2026: 625670 | MORROW-WOODVILLE RD | 528000 | 658600 | 625670 | 79200 | 98790 | Y
117604 | 10 | WAS-TR 298-0.54 | 8437505 | Y | X | 100 | 2027-04-01 | 27/4 |  | 2027: 1750424 | GRANTSVILLE RD D/B | 1910500 | 2210500 | 2210500 |  |  | N
| 10 | WAS-TR 319-0.02 | 8434751 | Y | X | 80 |  | 29 |  | 2029: 993380 | STILLE RD | 1241700 | 1477956 | 1182364.8 |  |  | N
120883 | 3 | WAY-CR 51-3.28 | 8532028 | Y | X | 95 | 2027-08-01 | 28/1 |  | 2028: 823270 |  | 866600 | 1064920 | 1011674 | 129990 | 159738 | N
119537 | 3 | WAY-CR 70-1.13 | 8547149 | N | X | 95 | 2026-04-01 | 26/4 |  | 2026: 804800 | DOYLESTOWN RD D/B | 1006000 | 1206900 | 1146555 | 150900 | 181035 | N
115791 | 3 | WAY-TR 101-1.94 | 8533962 | Y | X | 95 | 2026-07-01 | 27/1 |  | 2027: 753350 | LEHR RD D/B | 893000 | 1093000 | 1038350 | 133950 | 163950 | N
118423 | 3 | WAY-TR 436-0.50 | 8541590 | Y | X | 100 | 2026-01-30 | 26/2 |  | 2026: 820000 | BANK ST D/B | 902000 | 1152000 | 1152000 |  |  | N
122118 | 3 | WAY-TR 178-4.40 | 8532281 | Y | X | 95 | 2027-09-15 | 28/1 |  | 2028: 855385 |  | 900400 | 1100400 | 1045380 | 135065 | 165060 | N
113921 | 2 | WIL-CR 16-0.12 | 8630038 | Y | X | 95 | 2025-07-07 | 26/1 |  | 2026: 867445 | Rehab | 826000 | 1016200 | 965390 | 123900 | 152430 | Y
119450 | 2 | WOO-CR 3F-0.02 | 8731004 | Y | X | 100 | 2026-07-01 | 27/1 |  | 2027: 391000 | CYGNET RD Rehab | 391000 | 516000 | 516000 |  |  | N
113924 | 2 | WOO-CR 82D-7.69 | 8746354 | N | X | 80 | 2025-07-07 | 26/1 |  | 2026: 673246 | HUFFMAN RD | 1069000 | 1279350 | 1023480 |  |  | Y
120882 | 1 | WYA-CR 16-6.04 | 8831688 | Y | X | 95 | 2027-09-24 | 28/1 |  | 2028: 2320280 |  | 2442400 | 2786640 | 2647308 | 366360 | 417996 | Y
122371 |  | STW 2025 CEAO LOAD RATING | [7 empty] | 2026: 1747097
122371 |  | STW 2025 CEAO LOAD RATING ENC | [7 empty] | 2026: 512404
|  | STW AASHTOWARE | [7 empty] | 301875 | 301875 | 301875 | 301875 | 301875
122368 |  | STW 2025 CEAO AASHTOWARE
VAR | - | PE, RW, GEO, GES TASK ORDERS ENCUMBERED- | [7 empty] | 2026: 1273005
VAR |  | FED/STATE CHANGE ORDERS ENC | [7 empty] | 2026: 111813
VAR | - | CO'S ENCUMBERED TO DATE- | [7 empty] | 2026: 494047
[10 empty] | --------------- | --------------- | --------------- | --------------- | ---------------
|  | Total- | [7 empty] | 80289623 | 41953462 | 45809482 | 37638185 | 24594971 | 0
|  | Budgeted ('25 Carryover Included)- | [7 empty] | 80888139 | 34414074 | 34414074 | 34414074 | 34414074 | 34414074
|  | Annual Surplus/(Shortfall)- | [7 empty] | 598516 | -7539388 | -11395408 | -3224111 | 9819103 | 34414074
|  | Accum. Surplus/(Shortfall)- | [7 empty] | 598516 | -6940872 | -18336280 | -21560391 | -11741288 | 22672786
[9 empty] | FEDERAL - ON SYSTEM | 19286130 | 14487749 | 12912327 | 8622500 | 7556320 | 0
[9 empty] | FEDERAL - OFF SYSTEM | 39465327 | 16849333 | 15457540 | 19068975 | 8283262 | 0
[9 empty] | TOTAL | 58751457 | 31337082 | 28369867 | 27691475 | 15839582 | 0
[9 empty] | Budget | 59207168 | 21612199 | 21612199 | 21612199 | 21612199 | 21914074
[9 empty] | Annual Surplus/(Shortfall) | 455711 | -9724883 | -6757668 | -6079276 | 5772617 | 21914074
[9 empty] | Accum. Surplus/(Shortfall)- | 455711 | -9269172 | -16026840 | -22106116 | -16333499 | 5580575
[9 empty] | FEDERAL/STATE EXCHANGE PROGRAM PROJECTS - ON SYSTEM | 3339086 | 1817350 | 2279225 | 0 | 679250 | 0
[9 empty] | FEDERAL/STATE EXCHANGE PROGRAM PROJECTS - OFF SYSTEM | 13758839 | 8497155 | 14858515 | 9644835 | 7774264 | 0
[9 empty] | TOTAL | 17097925 | 10314505 | 17137740 | 9644835 | 8453514 | 0
[9 empty] | Budget | 17352543 | 12500000 | 12500000 | 12500000 | 12500000 | 12500000
[9 empty] | Annual Surplus/(Shortfall) | 142805 | 2185495 | -4637740 | 2855165 | 4046486 | 12500000
[9 empty] | Accum. Surplus/(Shortfall)- | 142805 | 2328300 | -2309440 | 545725 | 4592211 | 17092211

## ODOT Funds & Notes
ODOT Funds | FY 26 | FY 27 | FY 28 | FY 29 | FY 30 | FY 31
Original Allocation | 24914074 | 34414074 | 34414074 | 34414074 | 34414074 | 34414074
Fed/State Exchange (Proforma) | FY 26: -3000000
BFP (Proforma) | FY 26: 40000000
Fed/State Exchange Allocation | FY 26: 12500000
ODOT Loan (Proforma)
25 Carryforward to FY26 | FY 26: 1174137
24 Carryforward to FY26 | FY 26: 457420
23 Carryforward to FY26 | FY 26: 569677
22 Carryforward to FY26 | FY 26: 18896
21 Carryforward to FY26 | FY 26: 763400
ODOT Loan for FY25 4B87 Repay FY26 | FY 26: -1362008
25 Carryforward to FY26 (Fed/State) | FY 26: 3778620
24 Carryforward to FY26 (Fed/State) | FY 26: 64421
23 Carryforward to FY26 (Fed/State) | FY 26: 96509
22 Carryforward to FY26 (Fed/State) | FY 26: 86652
21 Carryforward to FY26 (Fed/State) | FY 26: 826341
NOTES:
ODOT Funds consists of the Original Allocation, any (unbalanced) Proforma payments, Funds for Fed/State Exchange, Proj. Carryforward (both Fed/State and Non), and any ODOT Loans
Budgeted is funding from ODOT plus any Proforma credit/loans from ODOT plus any carryforward from the prior FY
Annual Surplus/(Shortfall) is Budgeted Carryover minus FY Program Total
Accum. Surplus/(Shortfall) is prior year Annual Surplus plus FY Annual Surplus/(Shortfall)
Formula for K319 (Off-system, Not Fed/State) | FY 26: ***SUMIFS(K7:K303,E7:E303,"N",W7:W303,"N")***
Formula for K320 (On-system, Not Fed/State) | FY 26: ***SUMIFS(K7:K303,E7:E303,"Y",W7:W303,"N")***
Formula will need updated when new projects are contemplated to increase the row count
Be mindful that the first dataset reviewed needs adjusted to the FY for each formula
Formula for K329 (Off-system, Fed/State Exch.) | FY 26: ***SUMIFS(K7:K303,E7:E303,"N",W7:W303,"Y")***
Formula for K330 (On-system, Fed/State Exch.) | FY 26: ***SUMIFS(K7:K303,E7:E303,"Y",W7:W303,"Y")***
Formula will need updated when new projects are contemplated to increase the row count
Be mindful that the first dataset reviewed needs adjusted to the FY for each formula